## Budget to Actual
Sample Tract
50 Acres
BUDGET TO ACTUAL
| Initial | Post Bid | Change Orders | Previous | Costs this | Costs | Cost to
Estimated Development Costs | Budget | Budget | Revisions | Costs | Month | to Date | Complete | Final Cost
Land Cost | 2250000 | 2250000 | 0 | 2250000 | 0 | 2250000 | 0 | 2250000 | 50 | Acres
Rollback Taxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190 | Lots | 3.8 | DU/AC
Clearing and Grubbing | 100000 | 125000 | 10000 | 100000 | 21500 | 121500 | 13500 | 135000
WS&D Distribution | 1875000 | 1795000 | 50000 | 1300000 | 200000 | 1500000 | 345000 | 1845000
Detention Pond | 225000 | 245000 | -18750 | 203625 | 0 | 203625 | 22625 | 226250
Off-Site WS&D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Paving | 2425000 | 2675000 | -176500 | 200000 | 500000 | 700000 | 1798500 | 2498500
Off-Site Paving | 75000 | 73200 | 125000 | 0 | 50000 | 50000 | 148200 | 198200
Engineering - WS&D | 367500 | 357000 | 10000 | 285000 | 15000 | 300000 | 67000 | 367000
Engineering - Paving | 425000 | 475000 | 15000 | 310000 | 40000 | 350000 | 140000 | 490000
Engineering - Drainage Study | 25000 | 25000 | 0 | 25000 | 0 | 25000 | 0 | 25000
Engineering - Miscellaneous | 25000 | 25000 | 0 | 25000 | 0 | 25000 | 0 | 25000
MUD Bond Issue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Annexation Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase I Environmental Report | 5000 | 5000 | 0 | 5000 | 0 | 5000 | 0 | 5000
Wetlands Report | 2500 | 7500 | 25000 | 2500 | 0 | 2500 | 30000 | 32500
Materials Testing - WS&D | 63000 | 61200 | 0 | 50000 | 0 | 50000 | 11200 | 61200
Materials Testing - Paving | 75000 | 95000 | 0 | 5000 | 5000 | 10000 | 85000 | 95000
Geotechnical Report | 10000 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000
Entry Features (Includes Monument Sign) | 150000 | 150000 | 0 | 0 | 0 | 0 | 150000 | 150000
Greenbelts (Includes Trees & Irrigation) | 50000 | 50000 | 0 | 0 | 0 | 0 | 50000 | 50000
Removal of House, plugging of wells, etc… | 50000 | 65000 | 35000 | 100000 | 0 | 100000 | 0 | 100000
Legal Fees | 50000 | 50000 | 0 | 35000 | 0 | 35000 | 15000 | 50000
Development Management Fees | 95000 | 95000 | 0 | 0 | 0 | 0 | 95000 | 95000
Topography Survey | 10000 | 8750 | 0 | 7500 | 0 | 7500 | 1250 | 8750
Land Planning | 7500 | 7500 | 0 | 7500 | 0 | 7500 | 0 | 7500
SWPPP | 50000 | 50000 | 25000 | 15000 | 10000 | 25000 | 50000 | 75000
HOA Subsidy | 75000 | 75000 | 100000 | 0 | 0 | 0 | 175000 | 175000
Boundary Survey | 10000 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000
Development Loan Interest | 340000 | 340000 | 0 | 200000 | 50000 | 250000 | 90000 | 340000
Property Taxes | 250000 | 250000 | 0 | 95000 | 0 | 95000 | 155000 | 250000
Contingency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTALS | 9085500 | 9375150 | 199750 | 5241125 | 891500 | 6132625 | 3442275 | 9574900
[10 empty] | 50 | Lot Width
COST PER LOT | 47818.4211 | 49342.8947 | 1051.3158 | 27584.8684 | 4692.1053 | 32276.9737 | 18117.2368 | 50394.2105 | OR | 956.3684 | Per Front Foot
COST PER ACRE | 181710 | 187503 | 3995 | 104822.5 | 17830 | 122652.5 | 68845.5 | 191498
8700000
65%
5655000
2
6%
339300
Lots | 190
Acres | 50
Revisions are also known as Change Orders
How much did the Final Cost (per lot) increase/decrease from the Land Book Budget (per lot)? | [7 empty] | 1051.3158